## Instructions
The court CMS Service Requirements are presented in the Statement of Work in ATTACHMENT C. For each of the service requirements included in ATTACHMENT C, the Vendor must use this table to indicate how it will meet these requirements. The identification number and title for each court CMS requirement is entered into the tables that compose this ATTACHMENT D. The details of each requirement from ATTACHMENT C (in their entirety) are included herein by reference. Each category is included in a separate tab in the workbook. The table below provides an overview of these major categories:
Category | Description
Project Management | Requirements in this category outline specific management and control services associated with the implementation of court CMS.
System Design and Construction | Requirements in this category include all activities necessary to develop, assemble, and otherwise prepare the proposed system for implementation.
System Delivery | The solution provider will be required to provide three releases of court CMS: Pilot, Production Release 1, and Production Release 2. The solution provider will also be required to prepare an initial and a long-term release plan for court CMS.
System Implementation | System implementation services and deliverables include all of the activities necessary to configure and deploy the system.
Training | These services will include planning and coordination, development of training materials and tools, and delivery of training to State Bar IT, clerks, judges, and court administrators.
System Support | System support services include all of the activities necessary to maintain, efficiently update, and generally support the system in the event of technical or other issues.
For each of the service requirements (the details of which are included by reference), Vendor must indicate one of the following four responses in the column labeled “Response Code.” The response code column must be completed for each requirement for each worksheet included in this ATTACHMENT D workbook.
A – Proposing Extensions | The Vendor agrees to perform the services in the manner, scope, and schedule identified in ATTACHMENT C as a part of its proposed solution. In addition, Vendor proposes specific enhancements to these services (e.g., additional services, broader scope of stakeholders served, earlier completion). Vendor must list the enhancements in the comments for this item.
B – Agrees to Perform | The Vendor agrees to perform the services in the manner, scope, and schedule identified in ATTACHMENT C as a part of its proposed solution. No comment is required.
C – Proposing Alternative | The Vendor proposes to meet the intent of the specified services in an alternative manner. Vendor must explain why this alternative is in the best interest of the State Bar and the court and describe in detail the services provided, the scope of those services, and the time frame for delivery. Failure to provide that explanation in the Assumptions/Comments field would be considered nonresponsive and may be grounds for disqualification from the procurement.
F – Not Proposed | The Vendor does not propose to support the service requirement. An explanation as to why this is in the best interest of the State Bar and the court is required. Failure to provide that explanation in the Assumptions/Comments field would be considered nonresponsive and may be grounds for disqualification from the procurement.
In the event that “Requirement” text of any technical requirement is modified or deleted, the text for that requirement in this RFP ATTACHMENT D (and any subsequent amendment) shall supersede and replace the text for that requirement in any Vendor proposal. Material modification of a “Requirement" text field by the Vendor would be considered nonresponsive and may be grounds for disqualification from the procurement.

## Service Requirements
ID | Category | Requirement Title | Response Code | Assumptions/Comments
1.1 | PM | Prepare Project Management Plan
1.2 | PM | Provide Project Management
1.2.1 | PM | Produce Written Monthly Status Report
1.2.2 | PM | Conduct Monthly Status Meeting
2.1 | Sys D&C | Prepare court CMS Design, Configuration, and Construction Plan
2.2 | Sys D&C | Conduct Requirements Gap Analysis
2.3 | Sys D&C | Track Requirements to Implementation
2.4 | Sys D&C | Design court CMS
2.5 | Sys D&C | Perform System Testing
3.1 | Sys Del | Produce court CMS Pilot
3.2 | Sys Del | Produce Production court CMS Release 1
3.3 | Sys Del | Prepare Long-Term Release Plan
3.4 | Sys Del | Produce Production court CMS Release 2
4.1 | Sys Imp | Prepare Deployment Plan
4.2 | Sys Imp | Assist Configuration
4.3 | Sys Imp | Perform Data Conversion
4.4 | Sys Imp | Assist Testing
4.5 | Sys Imp | Support Production System Deployment
5.1 | Train | Plan for Training
5.2 | Train | Provide Predesign Training of Personnel
5.3 | Train | Provide court CMS User and Administrator Training
5.4 | Train | Produce Training Documentation
6.1 | Sys Sup | Version and Patch Release Management
6.2 | Sys Sup | Backup and Recovery Procedures and Tools
6.3 | Sys Sup | On-Site Support
6.4 | Sys Sup | Level 1 Help Desk Support
6.5 | Sys Sup | Ongoing Level 2 Support and Problem Resolution
6.6 | Sys Sup | Other Software and Hardware Maintenance

## Response Codes (hidden)
Proposing Extensions
Agrees to Perform
Proposing Alternative
Not Proposed